## Chapter example
Activity | ID | Duration | Predecessors | Start Date | End Date | Normal days | Crash days | Normal cost | Crash cost | Cost per day
Activity A | A | 3d |  | 2026-11-02 |  | 3 | 2 | 50 | 70 | 20
Activity B | B | 6d | 1 |  |  | 6 | 4 | 80 | 160 | 40
Activity C | C | 10d | 1 |  |  | 10 | 9 | 60 | 90 | 30
Activity D | D | 11d | 1 |  |  | 11 | 7 | 50 | 150 | 25
Activity E | E | 8d | 2 |  |  | 8 | 6 | 100 | 160 | 30
Activity F | F | 5d | 3, 4 |  |  | 5 | 4 | 40 | 70 | 30
Activity G | G | 6d | 5, 6 |  |  | 6 | 6 | 70 | 70 | 0