## Smartsheet Import
Task Name | WBS | Indent Level | Parent WBS | Estimate Method | Low Duration (days) | Likely Duration (days) | High Duration (days) | Duration Range (days) | Planned Effort (hours) | Labor Rate | Labor Cost | Nonlabor Cost | Cost Type | Contingency % | Total Estimate | Owner | Risk Level | Estimating Assumption
Two-Day Manufacturing Conference | 1 | 0 |  | Bottom-up rollup |  |  |  |  | 380 |  | 26140 | 46000 |  |  | 82511 | Sponsor and Project Manager | Summary | Rollup of child work packages.
Project management | 1.1 | 1 | 1 | Bottom-up rollup |  |  |  |  | 42 |  | 3570 | 500 |  |  | 4477 | Project Manager | Summary | Rollup of child work packages.
Approvals and contracts | 1.1.1 | 2 | 1.1 | Expert judgment | 2 | 3 | 5 | 3 | 18 | 85 | 1530 | 500 | Direct project overhead | 10% | 2233 | Project Manager | Low | Standard university review cycle; no new legal clauses.
Status reporting | 1.1.2 | 2 | 1.1 | Template | 2 | 3 | 5 | 3 | 24 | 85 | 2040 | 0 | Direct project overhead | 10% | 2244 | Project Manager | Low | Weekly report template and dashboard already exist.
Venue and logistics | 1.2 | 1 | 1 | Bottom-up rollup |  |  |  |  | 48 |  | 3260 | 31500 |  |  | 39132 | Logistics Lead | Summary | Rollup of child work packages.
Venue selection | 1.2.1 | 2 | 1.2 | Delphi | 3 | 5 | 8 | 5 | 16 | 70 | 1120 | 9000 | Direct | 15% | 11638 | Logistics Lead | Medium | A campus venue is available for both event days.
Catering contract | 1.2.2 | 2 | 1.2 | Ratio | 2 | 4 | 7 | 5 | 12 | 70 | 840 | 16000 | Direct | 10% | 18524 | Logistics Lead | Medium | Catering serves 300 attendees at the quoted service level.
AV setup | 1.2.3 | 2 | 1.2 | Range | 2 | 4 | 8 | 6 | 20 | 65 | 1300 | 6500 | Direct | 15% | 8970 | AV Lead | Medium | Two rooms need recording; venue network passes load testing.
Registration system | 1.3 | 1 | 1 | Bottom-up rollup |  |  |  |  | 76 |  | 6120 | 3100 |  |  | 10957 | Systems Lead | Summary | Rollup of child work packages.
Configure platform | 1.3.1 | 2 | 1.3 | Parametric | 4 | 6 | 10 | 6 | 32 | 90 | 2880 | 2400 | Direct | 20% | 6336 | Systems Lead | Medium | Existing registration template supports required fields.
Payment testing | 1.3.2 | 2 | 1.3 | Template | 2 | 4 | 7 | 5 | 20 | 90 | 1800 | 0 | Direct | 20% | 2160 | Systems Lead | Medium | One payment gateway and two refund cases are in scope.
Attendee communications | 1.3.3 | 2 | 1.3 | Parametric | 3 | 5 | 8 | 5 | 24 | 60 | 1440 | 700 | Direct | 15% | 2461 | Communications Lead | Medium | Four scheduled campaigns use the existing email platform.
Program and speakers | 1.4 | 1 | 1 | Bottom-up rollup |  |  |  |  | 54 |  | 4050 | 3000 |  |  | 8362.5 | Program Lead | Summary | Rollup of child work packages.
Confirm speakers | 1.4.1 | 2 | 1.4 | Delphi | 6 | 10 | 18 | 12 | 28 | 75 | 2100 | 3000 | Direct | 20% | 6120 | Program Lead | High | Twelve speakers; two require travel support.
Session schedule | 1.4.2 | 2 | 1.4 | Template | 4 | 7 | 11 | 7 | 26 | 75 | 1950 | 0 | Direct | 15% | 2242.5 | Program Lead | High | Two tracks and sixteen sessions; no hybrid delivery.
Marketing | 1.5 | 1 | 1 | Bottom-up rollup |  |  |  |  | 60 |  | 3900 | 5700 |  |  | 11356 | Marketing Lead | Summary | Rollup of child work packages.
Creative assets | 1.5.1 | 2 | 1.5 | Parametric | 4 | 6 | 9 | 5 | 32 | 65 | 2080 | 1200 | Direct | 15% | 3772 | Marketing Lead | Medium | Eight reusable asset formats; brand templates are approved.
Campaign launch | 1.5.2 | 2 | 1.5 | Ratio | 5 | 8 | 12 | 7 | 28 | 65 | 1820 | 4500 | Direct | 20% | 7584 | Marketing Lead | High | Paid media mix matches the prior event.
Event delivery | 1.6 | 1 | 1 | Bottom-up rollup |  |  |  |  | 76 |  | 3920 | 2200 |  |  | 6802 | Operations Lead | Summary | Rollup of child work packages.
On-site staffing | 1.6.1 | 2 | 1.6 | Ratio | 2 | 3 | 4 | 2 | 56 | 45 | 2520 | 2200 | Direct | 10% | 5192 | Operations Lead | Low | Eight staff cover two event days under the approved shift plan.
Run of show | 1.6.2 | 2 | 1.6 | Expert judgment | 2 | 3 | 5 | 3 | 20 | 70 | 1400 | 0 | Direct | 15% | 1610 | Operations Lead | Low | One rehearsal and one control room are sufficient.
Closeout | 1.7 | 1 | 1 | Bottom-up rollup |  |  |  |  | 24 |  | 1320 | 0 |  |  | 1424.5 | Project Manager | Summary | Rollup of child work packages.
Reconcile invoices | 1.7.1 | 2 | 1.7 | Template | 2 | 3 | 5 | 3 | 14 | 55 | 770 | 0 | Direct project overhead | 10% | 847 | Finance Lead | Low | All vendors invoice within ten business days.
Lessons learned | 1.7.2 | 2 | 1.7 | Template | 1 | 2 | 3 | 2 | 10 | 55 | 550 | 0 | Direct project overhead | 5% | 577.5 | Project Manager | Low | Core team attends a 90-minute retrospective.

## Studio Guide
Studio 5: Conference Estimating Lab
Audience: IMSE 456/656 students. Target engine: Smartsheet.
Starting decision
Measure | Value | Interpretation
Top-down sponsor cap | 80000 | A decision threshold, not a task estimate
Bottom-up starting estimate | 82511 | Rollup of work-package labor, nonlabor, and contingency
Variance to cap | 2511 | Positive means the estimate exceeds the cap
Variance % | 3.139% | The initial estimate is 3.1% above the cap
Student workflow
1 | Import this workbook into Smartsheet and select the Smartsheet Import worksheet.
2 | Keep Task Name as the primary column. Indent rows using Indent Level and verify every Parent WBS.
3 | Format currency and percentage columns, then add the Smartsheet formulas from Formula Guide.
4 | Sort or filter for High risk. Improve at least three assumptions with a source, threshold, or condition.
5 | Re-estimate one high-risk work package with a second method and record why the result changed.
6 | Compare the revised bottom-up total with the $80,000 cap. Recommend scope change, additional funding, or acceptance.
Submission
Evidence | One screenshot showing hierarchy, formulas, and risk formatting
Sheet | Exported Smartsheet with the revised estimate
Decision | A 100-word recommendation explaining the cap variance and next action
Compatibility note | Smartsheet accepts Excel imports, but Excel formulas may not translate because formula syntax differs. This workbook therefore imports calculated values and provides Smartsheet-native formulas separately.
Source | https://help.smartsheet.com/articles/504553-import-files-to-create-new-sheets

## Formula Guide
Smartsheet formula guide
Add these as column formulas for leaf rows. Use SUM(CHILDREN()) only for additive summary fields.
Target column | Smartsheet formula | Purpose
Duration Range (days) | '=[High Duration (days)]@row - [Low Duration (days)]@row | High minus low
Labor Cost | '=[Planned Effort (hours)]@row * [Labor Rate]@row | Effort multiplied by rate
Total Estimate | '=([Labor Cost]@row + [Nonlabor Cost]@row) * (1 + [Contingency %]@row) | Cost including visible contingency
Summary Planned Effort | '=SUM(CHILDREN()) | Use in Planned Effort on parent rows
Summary Labor Cost | '=SUM(CHILDREN()) | Use in Labor Cost on parent rows
Summary Nonlabor Cost | '=SUM(CHILDREN()) | Use in Nonlabor Cost on parent rows
Summary Total Estimate | '=SUM(CHILDREN()) | Use in Total Estimate on parent rows
Hierarchy
Use the Indent Level column as a guide. Indent Level 1 under WBS 1, then Indent Level 2 under its matching Parent WBS. Smartsheet hierarchy uses indentation rather than the WBS code itself.
Official help | https://help.smartsheet.com/articles/504734-hierarchy-indenting-outdenting-rows