## Activities
Studio 9 · Conference activities, coordinators and cost
Week 6 network with two additions: coordinators needed while the activity runs, and its direct cost. Fill the yellow CPM cells (Week 6) before the Load sheet.
ID | Activity | Predecessors | Duration (days) | Coordinators | Cost ($) | Cost per day ($) | ES | EF | LS | LF | Total slack
A | Approve event brief | — | 2 | 1 | 2000
B | Contract venue | A | 5 | 2 | 30000
C | Draft program | A | 6 | 1 | 6000
D | Configure registration | B | 4 | 1 | 8000
E | Confirm speakers | C | 8 | 2 | 12000
F | Recruit exhibitors | C | 5 | 2 | 2500
G | Publish program | D, E | 3 | 1 | 3000
H | Prepare on-site materials | F, G | 4 | 2 | 4000
I | Complete rehearsal | H | 2 | 2 | 2500
Total
Project duration with unlimited coordinators (days)
Scenario 1: three coordinators. Scenario 2: two. Scenario 3: two, plus a third for five consecutive days of your choosing. Coordinators are interchangeable; an activity cannot be split once started.

## Load ES
Early-start load
Enter the ES values from the Activities sheet as the start days. This is the plan before anyone looks at the team.
ID | Coord. | Dur. | Start | Finish | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
A | 1 | 2
B | 2 | 5
C | 1 | 6
D | 1 | 4
E | 2 | 8
F | 2 | 5
G | 1 | 3
H | 2 | 4
I | 2 | 2
Load
Available |  |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Over by
Project finish (max Finish)
Peak load
Days over the limit
Enter each activity's start day (0 = project start). The grid shows the coordinators it uses on each day, the Load row sums them, and Over by flags any day above the limit.

## Level 3
Levelled to three coordinators
Apply the parallel method period by period. Priority: minimum slack, then shortest duration, then lowest ID. Record every decision in the Log sheet.
ID | Coord. | Dur. | Start | Finish | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
A | 1 | 2
B | 2 | 5
C | 1 | 6
D | 1 | 4
E | 2 | 8
F | 2 | 5
G | 1 | 3
H | 2 | 4
I | 2 | 2
Load
Available |  |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Over by
Project finish (max Finish)
Peak load
Days over the limit
Enter each activity's start day (0 = project start). The grid shows the coordinators it uses on each day, the Load row sums them, and Over by flags any day above the limit.

## Level 2
Levelled to two coordinators
Same method, two coordinators. Then compare your finish with the optimum from Part 3.
ID | Coord. | Dur. | Start | Finish | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
A | 1 | 2
B | 2 | 5
C | 1 | 6
D | 1 | 4
E | 2 | 8
F | 2 | 5
G | 1 | 3
H | 2 | 4
I | 2 | 2
Load
Available |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Over by
Project finish (max Finish)
Peak load
Days over the limit
Enter each activity's start day (0 = project start). The grid shows the coordinators it uses on each day, the Load row sums them, and Over by flags any day above the limit.

## Loan
Two coordinators plus a third for five days
Change five consecutive cells of the Available row from 2 to 3, then schedule against the new limits. Which window buys the earliest finish?
ID | Coord. | Dur. | Start | Finish | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
A | 1 | 2
B | 2 | 5
C | 1 | 6
D | 1 | 4
E | 2 | 8
F | 2 | 5
G | 1 | 3
H | 2 | 4
I | 2 | 2
Load
Available |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Over by
Project finish (max Finish)
Peak load
Days over the limit
Enter each activity's start day (0 = project start). The grid shows the coordinators it uses on each day, the Load row sums them, and Over by flags any day above the limit.

## Log
Levelling log · parallel method
One row per period in which you made a decision. Eligible activities, their slack at that moment, and what you started or delayed.
Scenario | Period t | In progress (coordinators used) | Eligible activities | Priority order and slack (LF − t − dur) | Started | Delayed | Reason

## Budget
Time-phased budget baseline
Cost per day comes from the Activities sheet. Enter each schedule's start days; the weekly spend and cumulative baseline calculate.
Schedule | Start A | B | C | D | E | F | G | H | I | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Total
Early start (ES)
Late start (LS)
Levelled, 3 coordinators
Levelled, 2 coordinators (yours)
Optimum, 2 coordinators (Part 3)
Two coordinators plus a 5-day loan (Part 3)
Cumulative
Schedule | [9 empty] | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8
Early start (ES)
Late start (LS)
Levelled, 3 coordinators
Levelled, 2 coordinators (yours)
Optimum, 2 coordinators (Part 3)
Two coordinators plus a 5-day loan (Part 3)
Status check: at the end of week 2 the sponsor has been invoiced $52,000. Against which baseline is that over, and what would you need to know before saying so? | bar: Wk 1

## Reconciliation
AI levelling · reconciliation
Gemini levels the two-coordinator case cold. Compare its schedule with yours and with the optimum, line by line.
Line | Your value | Model's value | Optimum | Who is right, and why | Change made
Finish day
Start of B
Start of C
Start of E
Peak coordinators
Any day over the limit?
Any predecessor violated?
Any activity split?
Where it put the five-day loan
Other