## Register
Studio 7 · Conference risk register
Fill the yellow cells. Rate L, I and D with the Scales sheet. RPN and Zone calculate. Write the register before using AI.
ID | RBS category | Threat or opportunity | Cause | Risk event | Effect | L | I | D | RPN | Zone | Response type | Response (done now) | Contingency plan (if it happens) | Trigger (observable) | Owner (role) | Reserve ($)
R1
R2
R3
R4
R5
R6
R7
R8
Total reserve

## Scales
Rating scales
Agree these definitions before you rate. Rate an event on the objective it hurts most.
Impact | 1 · Very low | 2 · Low | 3 · Moderate | 4 · High | 5 · Very high
Cost | Negligible | Under 10% over | 10–20% over | 20–40% over | Over 40% over
Time | Negligible | Under 5% late | 5–10% late | 10–20% late | Over 20% late
Scope | Barely noticed | Minor areas affected | Major areas affected | Sponsor would reject the reduction | Deliverable effectively useless
Quality | Barely noticed | Only the most demanding uses affected | Sponsor must approve the reduction | Sponsor would reject the reduction | Deliverable effectively useless
Likelihood | 1 · Rare | 2 · Unlikely | 3 · Possible | 4 · Likely | 5 · Almost certain
Chance it occurs | Under 10% | 10–30% | 30–50% | 50–80% | Over 80%
Detection difficulty | 1 · Obvious | 2 · Early warning | 3 · Some warning | 4 · Little warning | 5 · Hidden
When would we know? | Weeks ahead, by routine checks | Days ahead, if someone looks | Shortly before, with effort | Only as it happens | Only after the damage is done
Severity zones (used by the Register's Zone column)
Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
5 | Minor | Moderate | Moderate | Major | Major
4 | Minor | Moderate | Moderate | Major | Major
3 | Minor | Minor | Moderate | Moderate | Major
2 | Minor | Minor | Moderate | Moderate | Major
1 | Minor | Minor | Minor | Moderate | Moderate

## Matrix
Severity matrix
Risk IDs appear in the cell matching their likelihood (row) and impact (column).
Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
5
4
3
2
1
Dark: major · Mid: moderate · Light: minor. Impact weighs more than likelihood, so the major zone runs down the impact-5 column.

## PERT
PERT · revised three-point estimates (workdays)
These estimates replace the ones in the notes. Enter your own formulas in the yellow cells.
ID | Activity | Predecessors | a | m | b | t_e | Variance
A | Event brief | — | 2 | 2 | 8
B | Venue | A | 4 | 7 | 16
C | Program draft | A | 4 | 6 | 8
D | Registration | B | 3 | 5 | 13
E | Speakers | C | 6 | 8 | 16
F | Exhibitors | C | 2 | 5 | 8
G | Publish program | D, E | 3 | 3 | 9
H | Materials | F, G | 2 | 4 | 6
I | Rehearsal | H | 2 | 2 | 8
Paths
Path |  |  | Sum t_e | Sum variance | σ | Z at T_S | P(finish ≤ T_S)
A–B–D–G–H–I
A–C–E–G–H–I
A–C–F–H–I
Scheduled time T_S (sponsor's date) |  |  | 32
Z for 90% confidence |  |  | 1.2816
T_E + 1.28σ on the critical path
Tip: =NORM.S.DIST(Z, TRUE) returns the probability for a Z value.

## Reconciliation
AI review · reconciliation
One row per objection the model raised. If none of its objections hold, say so in row 1 and explain what you checked.
# | Objection (quote or summarize the model) | Accept or reject | Reason, tied to this project | Change made to the register
1
2
3
4
5
6
7
8
9
10