## Conference
Activity | ID | Duration | Predecessors | Start Date | End Date | Normal days | Crash days | Normal cost | Crash cost | Cost per day
Approve event brief | A | 2d |  | 2026-11-02 |  | 2 | 1 | 2000 | 3200 | 1200
Contract venue | B | 5d | 1 |  |  | 5 | 3 | 30000 | 31400 | 700
Draft program | C | 6d | 1 |  |  | 6 | 4 | 6000 | 6800 | 400
Configure registration | D | 4d | 2 |  |  | 4 | 3 | 8000 | 8900 | 900
Confirm speakers | E | 8d | 3 |  |  | 8 | 5 | 12000 | 13800 | 600
Recruit exhibitors | F | 5d | 3 |  |  | 5 | 3 | 2500 | 3100 | 300
Publish program | G | 3d | 4, 5 |  |  | 3 | 2 | 3000 | 4500 | 1500
Prepare on-site materials | H | 4d | 6, 7 |  |  | 4 | 2 | 4000 | 5600 | 800
Complete rehearsal | I | 2d | 8 |  |  | 2 | 2 | 2500 | 2500 | 0