## Smartsheet Import
Activity | ID | Duration | Predecessors | Assigned To | Allocation % | Cost | Coordinators needed
Approve event brief | A | 2d |  | Kim | 100 | 2000 | 1
Contract venue | B | 5d | 1 | Kim, Lee | 100 | 30000 | 2
Draft program | C | 6d | 1 | Ortiz | 100 | 6000 | 1
Configure registration | D | 4d | 2 | Kim | 100 | 8000 | 1
Confirm speakers | E | 8d | 3 | Lee, Ortiz | 100 | 12000 | 2
Recruit exhibitors | F | 5d | 3 | Kim, Lee | 100 | 2500 | 2
Publish program | G | 3d | 4, 5 | Kim | 100 | 3000 | 1
Prepare on-site materials | H | 4d | 6, 7 | Kim, Lee | 100 | 4000 | 2
Complete rehearsal | I | 2d | 8 | Lee, Ortiz | 100 | 2500 | 2
Import this tab. Predecessors are Smartsheet row numbers (A = row 1). Assigned To holds the early-start assignment of three coordinators; Allocation % is 100 per person.

## Formulas
Column or field | Where | Smartsheet formula | Note
Cost per day | column |  | Direct cost spread evenly over the activity's workdays
Workday start | column |  | 0 = project start; matches the notes' day numbers
Workday finish | column |  | Finish day as the notes count it
Wk 1 PV | column |  | Planned value in week 1: Mon 2 Nov to Fri 6 Nov
Wk 2 PV | column |  | Planned value in week 2: Mon 9 Nov to Fri 13 Nov
Wk 3 PV | column |  | Planned value in week 3: Mon 16 Nov to Fri 20 Nov
Wk 4 PV | column |  | Planned value in week 4: Mon 23 Nov to Fri 27 Nov
Wk 5 PV | column |  | Planned value in week 5: Mon 30 Nov to Fri 4 Dec
Wk 6 PV | column |  | Planned value in week 6: Mon 7 Dec to Fri 11 Dec
Wk 7 PV | column |  | Planned value in week 7: Mon 14 Dec to Fri 18 Dec
Wk 8 PV | column |  | Planned value in week 8: Mon 21 Dec to Fri 25 Dec
Project finish | Sheet Summary |  | Date type
Workdays | Sheet Summary |  | 25 on the early-start schedule
Wk n total | Sheet Summary |  | Weekly planned value
Cumulative to wk n | Sheet Summary |  | The baseline curve
Total cost | Sheet Summary |  | Must read $70,000 under every schedule
Smartsheet imports values, not formulas. Type each formula once in row 1, then right-click → Convert to Column Formula. Summary fields are typed in the Sheet Summary panel.
Formulas:
Smartsheet formula = Cost@row / NETWORKDAYS([Start Date]@row, [End Date]@row)
Smartsheet formula = NETWORKDAYS([Start Date]$1, [Start Date]@row) - 1