## Conference EVM
Activity | ID | Duration | Predecessors | Start Date | End Date | % Complete | Planned start | Planned days | Budget | Actual cost
Approve event brief | A | 2d |  | 2026-11-02 |  | 0% | 2026-11-02 | 2 | 2000 | 0
Contract venue | B | 5d | 1 |  |  | 0% | 2026-11-04 | 5 | 30000 | 0
Draft program | C | 6d | 1 |  |  | 0% | 2026-11-04 | 6 | 6000 | 0
Configure registration | D | 4d | 2 |  |  | 0% | 2026-11-11 | 4 | 8000 | 0
Confirm speakers | E | 8d | 3 |  |  | 0% | 2026-11-12 | 8 | 12000 | 0
Recruit exhibitors | F | 5d | 3 |  |  | 0% | 2026-11-12 | 5 | 2500 | 0
Publish program | G | 3d | 4, 5 |  |  | 0% | 2026-11-24 | 3 | 3000 | 0
Prepare on-site materials | H | 4d | 6, 7 |  |  | 0% | 2026-11-27 | 4 | 4000 | 0
Complete rehearsal | I | 2d | 8 |  |  | 0% | 2026-12-03 | 2 | 2500 | 0